**2/7 Meeting Notes**

To do eventually

* Redo all sources in IEEE and label figures accordingly
* Come up with hard questions that panelists will ask us and start preparing responses for them
  + Make google doc and add from now until April
* Finalize literature review

Updates from teams today

* Chapter 5 complete
  + Tyler moving to CH4, Brendan moving to CH3

Weekly Timeline for chapters

Finish writing by 3/7. Finalize thesis writing, citations, format by 3/14.

Dates are **when task is due**

* Chapter 1
  + 2/14: Comprehensive edit (Brendan)
  + 2/21: Final revisions (Tyler + Brendan)
  + 2/28: Sources in IEEE (Tyler)
* Chapter 2
  + 2/14: Sources in IEEE (Brendan + Cynthia)
  + 2/21: Comprehensive edit due (Aidan + Elizabeth)
  + 2/28: Final revisions due (Brendan + Cynthia)
* Chapter 3
  + 2/14: Finished chapter 3 ready for edits (Eric, Aidan, Elizabeth)
  + 2/21: Comprehensive edit due (Brendan)
  + 2/28: Final revisions due, sources in IEEE (Eric, Aidan, Elizabeth)
* Chapter 4
  + 2/14: Fill in theoretical analysis (Nathan and Rohith)
  + 2/21: Comprehensive Edits
  + 2/28:
  + 3/7:
* Chapter 5
  + 2/14: Sources in IEEE (Brendan)
  + 2/21: Comprehensive edit (Eric)
  + 2/28: Final revisions due (Brendan + Tyler)
* Justify why 3-point bend tests are sufficient
  + “Standard to both, but due to covid we selected to do bending tests”