## Sheet1
| 2/3-2/9 | 2/10-2/16 | 2/17-2/24 | 2/25-3/1 | 3/2-3/8 | 3/9-3/13 | SPRING BREAK | 3/23-3/29 | 3/30-4/5 | 4/6-4/12 | 4/13-4/19 | 4/20-4/26 | 4/27-5/3 | 5/4-5/10
Order and Recieve Parts
Work on thesis defense
Begin construction on head
Meet with structures to discuss dimensions
Run tests on extruder part only
Address problems with tests
Run integrated test (optimistic)