## Sheet1
| 2019-01-27 | 2019-02-03 | 2019-02-10 | 2019-02-17 | 2019-02-24 | 2019-03-03 | 2019-03-10 | 2019-03-17 | 2019-03-24 | 2019-03-31 | 2019-04-07 | 2019-04-14 | 2019-04-21 | 2019-04-28 | 2019-05-05 | 2019-05-12 | 2019-05-19 | 2019-05-26 | 2019-06-02 | 2019-06-09
3D Scanning
Obtain and Setup Scanner | bar: 2019-01-27 to 2019-04-07
Compare Ranging and Triangulation (using experimental research data) | bar: 2019-01-27 to 2019-02-03
Scanner design | bar: 2019-02-03 to 2019-02-17
Construct/Obtain Scanner | bar: 2019-02-17 to 2019-03-17
Write/Obtain software for converting point cloud to mesh | bar: 2019-02-17 to 2019-03-17
Test scanner for resolution and resolve noise | bar: 2019-03-10 to 2019-04-07
ToolPathing | bar: 2019-03-31 to 2019-06-09
Find Algorithms | bar: 2019-03-10 to 2019-04-14
Create Framework for Testing | bar: 2019-03-31 to 2019-04-14
Decide on method for minimum viable product | bar: 2019-04-14 to 2019-05-05
Implement and test MVP method | bar: 2019-05-05 to 2019-06-09
Adjusted
Obtain and Setup Scanner | bar: 2019-03-17 to 2019-05-26
Compare Ranging and Triangulation (using experimental research data) | bar: 2019-03-17 to 2019-03-24
Scanner design | bar: 2019-03-24 to 2019-04-07
Construct/Obtain Scanner | bar: 2019-04-07 to 2019-05-05
Write/Obtain software for converting point cloud to mesh | bar: 2019-04-07 to 2019-05-05
Test scanner for resolution and resolve noise | bar: 2019-04-28 to 2019-05-26
Find Algorithms | bar: 2019-04-07 to 2019-06-09
Create Framework for Testing | bar: 2019-03-17 to 2019-04-21
Decide on method for minimum viable product | bar: 2019-04-07 to 2019-04-21
Implement and test MVP method | bar: 2019-04-21 to 2019-05-12